## Result
ID | DU ID | DU Name | Link ID | Link Name | Link Type Name | Business Type | status | Spot-Check Approval Status | Site ID | Site Name | Site Type | Source ID | Total Item Quantity | Collected Item Quantity | Passed Item Quantity | Failed Item Quantity | Template Name | Intelligent Review | Intelligent Review Start Time | Intelligent Review End Time | Version Number | Submitted By | Save Start Time | Save End Time | First Submit to Approval Time | Review Start Time | Latest Review End Time | Actual Task Close Time | Document Generated Identifier | Document Generated By | Document Generation Time | Historical Approver | Current Approve | Next Approve | Task Owner | Activity ID | Activity Name | DU Region | Subcontractor Name | Create Time | Project Code | Distance of APP reviews and site(M) | Task Change Remark | lasted review end date（Huawei） | Collection Role | Manual Review Start Time | BBU Site ID | BBU Site Name | RRU Site ID | RRU Site Name
3002053185006 | 77_14238 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_14238 | 77_14238 |  | ISDP RolloutPlan | 43 | 42 | 40 | 0 | Metro MTS QC Plan | Y | 2021-07-16 04:37:32 | 2021-07-17 02:25:29 | V1.600000 |  | 2021-07-12 19:05:01 | 2021-07-19 12:34:19 | 2021-07-12 19:05:01 | 2021-07-14 05:15:03 | 2021-07-17 11:58:20 |  | N | [6 empty] | 3365789106 | Smart QC task(installation) | Metro |  | 2021-06-21 17:07:34 | 56A0A8L |  | Normal task | 2021-07-17 11:58:20 |  | 2021-07-14 05:15:03
3002053187006 | 77_14239 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_14239 | 77_14239 |  | ISDP RolloutPlan | 43 | 1 | 0 | 0 | Metro MTS QC Plan | N |  |  | V1.600000 |  | 2021-07-20 02:29:56 | 2021-07-20 05:19:38 | 2021-07-20 02:29:56 |  |  |  | N | [6 empty] | 3365727106 | Smart QC task(installation) | Metro |  | 2021-06-21 17:07:59 | 56A0A8L |  | Normal task
3002054761006 | 77_04076 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_4076 | 77_4076 |  | ISDP RolloutPlan | 13 | 10 | 6 | 1 | Pre-installation QC Plan | N |  |  | V2.100000 |  | 2021-07-15 13:40:07 | 2021-07-20 11:05:42 | 2021-07-15 13:40:07 | 2021-07-16 16:03:24 | 2021-07-16 16:48:48 |  | N | [6 empty] | 2402141106 | Hardware installation | MC |  | 2021-07-05 12:09:20 | 56A0A8L |  | Normal task | 2021-07-16 16:48:48 |  | 2021-07-16 16:03:24
3002054763006 | 77_04076 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_4076 | 77_4076 |  | ISDP RolloutPlan | 60 | 60 | 58 | 0 | Moscow SWAP QC Plan | Y | 2021-07-20 11:22:38 | 2021-07-20 11:22:40 | V3.600000 |  | 2021-07-16 14:22:15 | 2021-07-20 12:32:00 | 2021-07-16 14:22:15 | 2021-07-16 16:07:49 | 2021-07-20 12:15:30 |  | N | [6 empty] | 2402137106 | Smart QC task(installation) | MC |  | 2021-07-05 12:09:48 | 56A0A8L |  | Normal task | 2021-07-20 12:15:30 |  | 2021-07-16 16:07:49
3002054739006 | 77_14236 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_14236 | 77_14236 |  | ISDP RolloutPlan | 43 | 31 | 26 | 3 | Metro MTS QC Plan | Y | 2021-07-17 03:56:41 | 2021-07-17 03:56:59 | V1.600000 |  | 2021-07-16 02:31:27 | 2021-07-17 04:18:11 | 2021-07-16 02:31:27 | 2021-07-17 03:56:41 | 2021-07-19 14:13:21 |  | N | [6 empty] | 3365899106 | Smart QC task(installation) | Metro |  | 2021-07-05 12:09:52 | 56A0A8L |  | Normal task | 2021-07-19 14:13:21 |  | 2021-07-17 11:58:48
3302261385006 | 77_15232 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_15232 | 77_15232 |  | ISDP RolloutPlan | 38 | 7 | 1 | 0 | Site Cleanup QC plan | N |  |  | V2.600000 |  | 2021-07-11 13:04:33 | 2021-07-12 07:00:02 | 2021-07-11 13:04:33 | 2021-07-12 07:00:50 | 2021-07-12 07:00:50 |  | N | [6 empty] | 13494948106 | Site Cleanup | MO |  | 2021-07-11 09:01:51 | 56A0A8L |  | Normal task | 2021-07-12 07:00:50 |  | 2021-07-12 07:00:50
3302261952006 | 77_03531 |  |  |  |  | QC-TE Operation quality | Pass With Minor Issues |  | PL_77_3531 | 77_3531 |  | ISDP RolloutPlan | 60 | 60 | 58 | 2 | Moscow SWAP QC Plan | Y | 2021-07-13 17:43:25 | 2021-07-13 17:43:25 | V3.6 |  | 2021-07-13 17:31:59 | 2021-07-20 08:34:10 | 2021-07-13 17:31:59 | 2021-07-13 17:43:25 | 2021-07-20 08:34:10 |  | N | [6 empty] | 2397607106 | Smart QC task(installation) | MC |  | 2021-07-12 13:04:25 | 56A0A8L |  | Normal task | 2021-07-14 15:52:58 |  | 2021-07-13 18:09:11
3302262052006 | 77_04100 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_4100 | 77_4100 |  | ISDP RolloutPlan | 60 | 60 | 59 | 0 | Moscow SWAP QC Plan | Y | 2021-07-17 17:35:04 | 2021-07-17 17:35:04 | V3.6 |  | 2021-07-17 02:01:21 | 2021-07-17 18:38:56 | 2021-07-17 02:01:21 | 2021-07-17 11:40:29 | 2021-07-17 18:44:30 |  | N | [6 empty] | 2450226106 | Smart QC task(installation) | MC |  | 2021-07-12 16:18:24 | 56A0A8L |  | Normal task | 2021-07-17 18:44:30 |  | 2021-07-17 11:40:29
3302262075006 | 77_12564 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_12564 | 77_12564 |  | ISDP RolloutPlan | 47 | 45 | 43 | 1 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-14 08:31:51 | 2021-07-19 21:30:31 | 2021-07-14 08:31:51 | 2021-07-14 19:40:15 | 2021-07-19 20:27:56 |  | N | [6 empty] | 2609809106 | Smart QC task(installation) | MC |  | 2021-07-12 16:21:14 | 56A0A8L |  | Normal task | 2021-07-19 20:27:56 |  | 2021-07-14 19:40:15
3302262167006 | 77_10898 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_10898 | 77_10898 |  | ISDP RolloutPlan | 47 | 47 | 41 | 5 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-13 09:07:57 | 2021-07-19 21:25:42 | 2021-07-13 09:07:57 | 2021-07-13 13:53:28 | 2021-07-16 11:40:19 |  | N | [6 empty] | 2604633106 | Smart QC task(installation) | MC |  | 2021-07-12 22:35:21 | 56A0A8L |  | Normal task | 2021-07-16 11:41:48 |  | 2021-07-13 13:53:28
3302262155006 | 77_10173 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_10173 | 77_10173 |  | ISDP RolloutPlan | 11 | 11 | 10 | 0 | Lamp Pole Painting | N |  |  | V1.2 |  | 2021-07-13 23:33:27 | 2021-07-16 11:06:17 | 2021-07-13 23:33:27 | 2021-07-14 11:38:23 | 2021-07-14 11:40:43 |  | N | [6 empty] | 11748793106 | Lamp Pole Painting | MC |  | 2021-07-12 23:06:52 | 56A0A8L |  | Normal task | 2021-07-14 11:40:43 |  | 2021-07-14 11:38:23
3302262129006 | 77_10173 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_10173 | 77_10173 |  | ISDP RolloutPlan | 38 | 16 | 13 | 2 | Site Cleanup QC plan | N |  |  | V2.6 |  | 2021-07-13 23:49:11 | 2021-07-16 12:54:15 | 2021-07-13 23:49:11 | 2021-07-14 13:00:22 | 2021-07-16 12:49:52 |  | N | [6 empty] | 2283121106 | Site Cleanup | MC |  | 2021-07-12 23:06:59 | 56A0A8L |  | Normal task | 2021-07-16 12:49:52 |  | 2021-07-14 13:00:22
3302262352006 | 77_14888 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_14888 | 77_14888 |  | ISDP RolloutPlan | 47 | 47 | 37 | 9 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-14 12:10:00 | 2021-07-19 10:43:39 | 2021-07-14 12:10:00 | 2021-07-14 12:41:12 | 2021-07-15 11:50:56 |  | N | [6 empty] | 2617248106 | Smart QC task(installation) | MC |  | 2021-07-13 11:38:19 | 56A0A8L |  | Normal task | 2021-07-15 11:52:24 |  | 2021-07-14 12:41:12
3302262547006 | 77_14539 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_14539 | 77_14539 |  | ISDP RolloutPlan | 38 | 37 | 15 | 4 | Site Cleanup QC plan | N |  |  | V2.6 |  | 2021-07-17 13:41:26 | 2021-07-18 11:41:02 | 2021-07-17 13:41:26 | 2021-07-18 11:14:37 | 2021-07-18 23:03:41 |  | N | [6 empty] | 2426562106 | Site Cleanup | MC |  | 2021-07-13 14:09:25 | 56A0A8L |  | Normal task | 2021-07-18 23:05:13 |  | 2021-07-18 11:14:37
3302262725006 | 77_10563 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_10563 | 77_10563 |  | ISDP RolloutPlan | 47 | 47 | 45 | 1 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-14 07:20:38 | 2021-07-20 09:13:22 | 2021-07-14 07:20:38 | 2021-07-14 12:37:30 | 2021-07-16 20:39:40 |  | N | [6 empty] | 2698362106 | Smart QC task(installation) | MC |  | 2021-07-13 23:30:00 | 56A0A8L |  | Normal task | 2021-07-16 20:39:40 |  | 2021-07-14 12:37:30
3302262866006 | 77_10363 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_10363 | 77_10363 |  | ISDP RolloutPlan | 47 | 17 | 13 | 1 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-15 08:14:59 | 2021-07-15 21:16:20 | 2021-07-15 08:14:59 | 2021-07-15 10:31:58 | 2021-07-15 23:18:41 |  | N | [6 empty] | 2373582106 | Smart QC task(installation) | MO |  | 2021-07-14 11:07:44 | 56A0A8L |  | Normal task | 2021-07-15 23:18:41 |  | 2021-07-15 10:31:58
3302262829006 | 77_15108 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_15108 | 77_15108 |  | ISDP RolloutPlan | 47 | 45 | 36 | 7 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-15 12:10:01 | 2021-07-16 14:04:57 | 2021-07-15 12:10:01 | 2021-07-15 18:15:16 | 2021-07-16 14:04:50 |  | N | [6 empty] | 2664078106 | Smart QC task(installation) | MC |  | 2021-07-14 11:38:15 | 56A0A8L |  | Normal task | 2021-07-16 14:06:19 |  | 2021-07-15 18:15:16
3302262830006 | 77_15157 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_15157 | 77_15157 |  | ISDP RolloutPlan | 47 | 32 | 19 | 0 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-15 10:10:11 | 2021-07-17 17:12:10 | 2021-07-15 10:10:11 | 2021-07-15 17:56:14 | 2021-07-16 14:51:32 |  | N | [6 empty] | 2666345106 | Smart QC task(installation) | MC |  | 2021-07-14 11:38:17 | 56A0A8L |  | Normal task | 2021-07-16 14:51:32 |  | 2021-07-15 17:56:14
3302262792006 | 77_15157 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_15157 | 77_15157 |  | ISDP RolloutPlan | 11 | 10 | 0 | 0 | Lamp Pole Painting | N |  |  | V1.2 |  | 2021-07-16 14:08:43 | 2021-07-17 17:11:57 | 2021-07-16 14:08:43 |  |  |  | N | [6 empty] | 11752863106 | Lamp Pole Painting | MC |  | 2021-07-14 11:42:50 | 56A0A8L |  | Normal task
3302262907006 | 77_03738 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_3738 | 77_3738 |  | ISDP RolloutPlan | 38 | 1 | 0 | 0 | Site Cleanup QC plan | N |  |  | V2.600000 |  | 2021-07-14 14:29:14 | 2021-07-14 14:29:16 | 2021-07-14 14:29:14 |  |  |  | N | [6 empty] | 13564348106 | Site Cleanup | MC |  | 2021-07-14 13:26:37 | 56A0A8L |  | Normal task
3302262860006 | 77_14852 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_14852 | 77_14852 |  | ISDP RolloutPlan | 11 | 11 | 0 | 0 | Lamp Pole Painting | N |  |  | V1.2 |  | 2021-07-20 03:10:40 | 2021-07-20 05:07:56 | 2021-07-20 03:10:40 |  |  |  | N | [6 empty] | 11751926106 | Lamp Pole Painting | MC |  | 2021-07-14 15:52:58 | 56A0A8L |  | Owner changed
3302263026006 | 77_14852 |  |  |  |  | QC-TE Operation quality | Pass With Minor Issues |  | PL_77_14852 | 77_14852 |  | ISDP RolloutPlan | 5 | 5 | 4 | 1 | EHS documents (документы по ОТ) | N |  |  | V1.0 |  | 2021-07-15 10:02:14 | 2021-07-16 10:48:57 | 2021-07-15 10:02:14 | 2021-07-15 16:32:27 | 2021-07-16 10:48:57 |  | N | [6 empty] | 11765125106 | EHS documents check | MC |  | 2021-07-14 15:54:23 | 56A0A8L |  | Owner changed | 2021-07-15 16:33:57 |  | 2021-07-15 16:32:27
3302263027006 | 77_14852 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_14852 | 77_14852 |  | ISDP RolloutPlan | 47 | 44 | 29 | 7 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-15 09:02:56 | 2021-07-20 09:15:27 | 2021-07-15 09:02:56 | 2021-07-15 12:23:54 | 2021-07-20 12:39:13 |  | N | [6 empty] | 2615615106 | Smart QC task(installation) | MC |  | 2021-07-14 15:56:31 | 56A0A8L |  | Owner changed | 2021-07-20 12:40:45 |  | 2021-07-15 12:23:54
3302263191006 | 77_10897 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_10897 | 77_10897 |  | ISDP RolloutPlan | 47 | 47 | 29 | 2 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-15 08:57:40 | 2021-07-19 21:10:00 | 2021-07-15 08:57:40 | 2021-07-15 18:07:19 | 2021-07-16 09:24:01 |  | N | [6 empty] | 2604854106 | Smart QC task(installation) | MC |  | 2021-07-15 00:18:34 | 56A0A8L |  | Normal task | 2021-07-16 09:24:01 |  | 2021-07-15 18:07:19
3302263289006 | 77_13068 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_13068 | 77_13068 |  | ISDP RolloutPlan | 38 | 32 | 28 | 3 | Site Cleanup QC plan | N |  |  | V2.6 |  | 2021-07-15 09:21:00 | 2021-07-16 08:33:33 | 2021-07-15 09:21:00 | 2021-07-15 14:36:41 | 2021-07-15 17:19:25 |  | N | [6 empty] | 2424030106 | Site Cleanup | MC |  | 2021-07-15 08:54:35 | 56A0A8L |  | Normal task | 2021-07-15 17:20:53 |  | 2021-07-15 14:36:41
3302263352006 | 77_15533 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_15533 | 77_15533 |  | ISDP RolloutPlan | 38 | 36 | 3 | 0 | Site Cleanup QC plan | N |  |  | V2.6 |  | 2021-07-15 11:29:04 | 2021-07-15 17:46:10 | 2021-07-15 11:29:04 | 2021-07-15 12:00:33 | 2021-07-15 12:01:09 |  | N | [6 empty] | 2353198106 | Site Cleanup | MC |  | 2021-07-15 10:55:05 | 56A0A8L |  | Normal task | 2021-07-15 12:01:09 |  | 2021-07-15 12:00:33
3302263486006 | 77_16753 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_16753 | 77_16753 |  | ISDP RolloutPlan | 47 | 44 | 27 | 6 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-16 10:42:50 | 2021-07-20 11:44:10 | 2021-07-16 10:42:50 | 2021-07-16 12:34:26 | 2021-07-20 12:49:07 |  | N | [6 empty] | 2707812106 | Smart QC task(installation) | MC |  | 2021-07-15 12:56:08 | 56A0A8L |  | Normal task | 2021-07-20 12:50:40 |  | 2021-07-16 12:34:26
3302263354006 | 77_16753 |  |  |  |  | QC-TE Operation quality | Pass With Minor Issues |  | PL_77_16753 | 77_16753 |  | ISDP RolloutPlan | 5 | 5 | 4 | 1 | EHS documents (документы по ОТ) | N |  |  | V1.0 |  | 2021-07-16 13:42:55 | 2021-07-19 23:40:43 | 2021-07-16 13:42:55 | 2021-07-17 15:35:42 | 2021-07-19 23:40:43 |  | N | [6 empty] | 11767158106 | EHS documents check | MC |  | 2021-07-15 12:56:57 | 56A0A8L |  | Normal task | 2021-07-17 15:36:49 |  | 2021-07-17 15:35:42
3302263665006 | 77_20400 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_20400 | 77_20400 |  | ISDP RolloutPlan | 38 | 5 | 3 | 0 | Site Cleanup QC plan | N |  |  | V2.600000 |  | 2021-07-18 16:40:44 | 2021-07-18 18:43:06 | 2021-07-18 16:40:44 | 2021-07-18 18:13:56 | 2021-07-18 18:43:27 |  | N | [6 empty] | 13563352106 | Site Cleanup | MO |  | 2021-07-15 17:36:31 | 56A0A8L |  | Normal task | 2021-07-18 18:43:27 |  | 2021-07-18 18:13:56
3302263785006 | 77_02342 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_2342 | 77_2342 |  | ISDP RolloutPlan | 47 | 44 | 42 | 2 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-16 21:39:09 | 2021-07-20 12:10:44 | 2021-07-16 21:39:09 | 2021-07-18 10:25:38 | 2021-07-20 12:23:57 |  | N | [6 empty] | 2481746106 | Smart QC task(installation) | MC |  | 2021-07-15 23:58:16 | 56A0A8L |  | Normal task | 2021-07-20 12:23:57 |  | 2021-07-18 10:25:38
3302263807006 | 77_14294 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_14294 | 77_14294 |  | ISDP RolloutPlan | 47 | 44 | 29 | 0 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-16 10:44:44 | 2021-07-19 14:38:02 | 2021-07-16 10:44:44 | 2021-07-16 14:45:18 | 2021-07-16 21:04:49 |  | N | [6 empty] | 2301333106 | Smart QC task(installation) | MC |  | 2021-07-15 23:58:24 | 56A0A8L |  | Normal task | 2021-07-16 21:04:49 |  | 2021-07-16 14:45:18
3302263846006 | 77_12114 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_12114 | 77_12114 |  | ISDP RolloutPlan | 38 | 1 | 0 | 0 | Site Cleanup QC plan | N |  |  | V2.600000 |  | 2021-07-16 17:26:47 | 2021-07-16 18:49:24 | 2021-07-16 17:26:47 |  |  |  | N | [6 empty] | 2245842106 | Hardware installation | MO |  | 2021-07-16 07:02:59 | 56A0A8L |  | Normal task
3302263847006 | 77_11237 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_11237 | 77_11237 |  | ISDP RolloutPlan | 47 | 27 | 20 | 5 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-17 09:19:32 | 2021-07-20 12:47:26 | 2021-07-17 09:19:32 | 2021-07-17 20:32:54 | 2021-07-20 12:53:45 |  | N | [6 empty] | 2419198106 | Smart QC task(installation) | MO |  | 2021-07-16 07:15:16 | 56A0A8L |  | Normal task | 2021-07-20 12:53:45 |  | 2021-07-17 20:32:54
3302263826006 | 77_13936 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_13936 | 77_13936 |  | ISDP RolloutPlan | 47 | 24 | 18 | 1 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-16 08:25:46 | 2021-07-18 03:46:04 | 2021-07-16 08:25:46 | 2021-07-16 09:37:26 | 2021-07-16 16:20:49 |  | N | [6 empty] | 2660493106 | Smart QC task(installation) | MO |  | 2021-07-16 07:15:18 | 56A0A8L |  | Normal task | 2021-07-16 16:20:49 |  | 2021-07-16 09:37:26
3302263885006 | 77_14356 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_14356 | 77_14356 |  | ISDP RolloutPlan | 47 | 13 | 2 | 0 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-18 09:13:40 | 2021-07-20 11:01:47 | 2021-07-18 09:13:40 |  |  |  | N | [6 empty] | 2254860106 | Smart QC task(installation) | MO |  | 2021-07-16 07:15:23 | 56A0A8L |  | Normal task
3302263886006 | 77_14835 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_14835 | 77_14835 |  | ISDP RolloutPlan | 47 | 43 | 38 | 4 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-16 14:24:27 | 2021-07-19 12:05:17 | 2021-07-16 14:24:27 | 2021-07-16 16:33:18 | 2021-07-19 12:05:35 |  | N | [6 empty] | 2614463106 | Smart QC task(installation) | MO |  | 2021-07-16 07:15:25 | 56A0A8L |  | Normal task | 2021-07-19 12:05:35 |  | 2021-07-16 16:33:18
3302264087006 | 77_14922 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_14922 | 77_14922 |  | ISDP RolloutPlan | 47 | 22 | 18 | 2 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-19 08:58:45 | 2021-07-20 12:52:20 | 2021-07-19 08:58:45 | 2021-07-19 18:28:39 | 2021-07-20 12:29:07 |  | N | [6 empty] | 2567038106 | Smart QC task(installation) | MC |  | 2021-07-16 17:48:18 | 56A0A8L |  | Normal task | 2021-07-20 12:29:07 |  | 2021-07-19 18:28:39
3302264089006 | 77_16859 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_16859 | 77_16859 |  | ISDP RolloutPlan | 47 | 46 | 19 | 4 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-19 07:52:42 | 2021-07-20 05:47:58 | 2021-07-19 07:52:42 | 2021-07-19 14:49:15 | 2021-07-19 21:59:18 |  | N | [6 empty] | 2620023106 | Smart QC task(installation) | MC |  | 2021-07-16 17:52:31 | 56A0A8L |  | Normal task | 2021-07-19 21:59:18 |  | 2021-07-19 14:49:15
3302264465006 | 77_05917 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_5917 | 77_5917 |  | ISDP RolloutPlan | 60 | 4 | 2 | 1 | Moscow SWAP QC Plan | N |  |  | V3.600000 |  | 2021-07-19 10:19:04 | 2021-07-19 21:48:59 | 2021-07-19 10:19:04 | 2021-07-19 18:13:01 | 2021-07-19 18:13:57 |  | N | [6 empty] | 2592402106 | Smart QC task(installation) | MO |  | 2021-07-18 09:43:25 | 56A0A8L |  | Owner changed | 2021-07-19 18:13:57 |  | 2021-07-19 18:13:01
3302264567006 | 77_02478 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_2478 | 77_2478 |  | ISDP RolloutPlan | 47 | 27 | 16 | 8 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-19 11:12:39 | 2021-07-19 17:39:04 | 2021-07-19 11:12:39 | 2021-07-20 07:59:28 | 2021-07-20 08:05:15 |  | N | [6 empty] | 2485789106 | Smart QC task(installation) | MC |  | 2021-07-19 00:28:51 | 56A0A8L |  | Normal task | 2021-07-20 08:06:47 |  | 2021-07-20 07:59:28
3302264587006 | 77_11957 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_11957 | 77_11957 |  | ISDP RolloutPlan | 47 | 11 | 8 | 1 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-19 11:14:34 | 2021-07-19 18:30:30 | 2021-07-19 11:14:34 | 2021-07-19 11:52:03 | 2021-07-20 08:14:34 |  | N | [6 empty] | 2469811106 | Smart QC task(installation) | MC |  | 2021-07-19 00:28:58 | 56A0A8L |  | Normal task | 2021-07-20 08:14:34 |  | 2021-07-19 11:52:03
3302264766006 | 77_12903 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_12903 | 77_12903 |  | ISDP RolloutPlan | 38 | 2 | 0 | 0 | Site Cleanup QC plan | N |  |  | V2.600000 |  | 2021-07-19 16:41:20 | 2021-07-19 17:34:04 | 2021-07-19 16:41:20 |  |  |  | N | [6 empty] | 2511349106 | Hardware installation | MO |  | 2021-07-19 09:17:05 | 56A0A8L |  | Normal task
3302264787006 | 77_12847 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_12847 | 77_12847 |  | ISDP RolloutPlan | 38 | 38 | 37 | 0 | Site Cleanup QC plan | N |  |  | V2.6 |  | 2021-07-19 13:52:55 | 2021-07-19 17:11:13 | 2021-07-19 13:52:55 | 2021-07-19 14:28:10 | 2021-07-19 17:11:57 |  | N | [6 empty] | 2561238106 | Site Cleanup | MO |  | 2021-07-19 09:20:02 | 56A0A8L |  | Normal task | 2021-07-19 17:11:57 |  | 2021-07-19 14:28:10
3302264869006 | 77_02341 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_2341 | 77_2341 |  | ISDP RolloutPlan | 60 | 1 | 0 | 0 | Moscow SWAP QC Plan | N |  |  | V3.6 |  | 2021-07-20 12:55:08 | 2021-07-20 12:55:10 | 2021-07-20 12:55:08 |  |  |  | N | [6 empty] | 2481300106 | Smart QC task(installation) | MC |  | 2021-07-19 11:45:00 | 56A0A8L |  | Normal task
3302265186006 | 77_10362 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_10362 | 77_10362 |  | ISDP RolloutPlan | 5 | 3 | 0 | 0 | EHS documents (документы по ОТ) | N |  |  | V1.0 |  | 2021-07-20 10:39:58 | 2021-07-20 10:40:47 | 2021-07-20 10:39:58 |  |  |  | N | [6 empty] | 11762636106 | EHS documents check | MO |  | 2021-07-19 22:05:47 | 56A0A8L |  | Normal task
3302265169006 | 77_10362 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_10362 | 77_10362 |  | ISDP RolloutPlan | 13 | 6 | 0 | 0 | Pre-installation QC Plan | N |  |  | V2.1 |  | 2021-07-20 11:01:41 | 2021-07-20 11:53:42 | 2021-07-20 11:01:41 |  |  |  | N | [6 empty] | 2373540106 | Hardware installation | MO |  | 2021-07-19 22:06:12 | 56A0A8L |  | Normal task
3302265170006 | 77_17154 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_17154 | 77_17154 |  | ISDP RolloutPlan | 47 | 5 | 2 | 0 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-20 10:11:14 | 2021-07-20 12:24:38 | 2021-07-20 10:11:14 |  |  |  | N | [6 empty] | 2438729106 | Smart QC task(installation) | MO |  | 2021-07-19 22:37:22 | 56A0A8L |  | Normal task
3302265230006 | 77_10259 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_10259 | 77_10259 |  | ISDP RolloutPlan | 5 | 3 | 0 | 0 | EHS documents (документы по ОТ) | N |  |  | V1.0 |  | 2021-07-20 09:07:19 | 2021-07-20 10:07:57 | 2021-07-20 09:07:19 |  |  |  | N | [6 empty] | 11759993106 | EHS documents check | MC |  | 2021-07-20 00:34:04 | 56A0A8L |  | Normal task
3302265179006 | 77_10259 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_10259 | 77_10259 |  | ISDP RolloutPlan | 47 | 5 | 2 | 0 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-20 11:07:29 | 2021-07-20 11:47:32 | 2021-07-20 11:07:29 |  |  |  | N | [6 empty] | 2328026106 | Smart QC task(installation) | MC |  | 2021-07-20 00:35:14 | 56A0A8L |  | Normal task
3302265180006 | 77_12088 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_12088 | 77_12088 |  | ISDP RolloutPlan | 47 | 12 | 2 | 0 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-20 08:31:42 | 2021-07-20 12:17:02 | 2021-07-20 08:31:42 |  |  |  | N | [6 empty] | 2292032106 | Smart QC task(installation) | MC |  | 2021-07-20 00:35:16 | 56A0A8L |  | Normal task
3302265367006 | 77_13365 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_13365 | 77_13365 |  | ISDP RolloutPlan | 42 | 5 | 1 | 0 | Site Cleanup QC plan | N |  |  | V2.6 |  | 2021-07-20 10:07:19 | 2021-07-20 12:16:46 | 2021-07-20 10:07:19 | 2021-07-20 12:55:28 | 2021-07-20 12:55:28 |  | N | [6 empty] | 2376464106 | Site Cleanup | MO |  | 2021-07-20 09:08:18 | 56A0A8L |  | Normal task | 2021-07-20 12:55:28 |  | 2021-07-20 12:55:28
3002039627006 | 77_00609 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_609 | 77_609 |  | ISDP RolloutPlan | 13 | 13 | 11 | 2 | Pre-installation QC Plan | N |  |  | V1.900000 |  | 2020-12-14 09:29:45 | 2021-02-02 13:42:34 | 2020-12-14 09:29:45 | 2020-12-14 10:12:35 | 2020-12-17 19:14:39 |  | N | [6 empty] | 2713709106 | Hardware installation | MO |  | 2020-12-11 13:25:53 | 56A0A8L |  | Normal task | 2020-12-17 19:14:39 |  | 2020-12-14 10:12:35
3002040542006 | 77_11140 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_11140 | 77_11140 |  | ISDP RolloutPlan | 13 | 13 | 12 | 1 | Pre-installation QC Plan | N |  |  | V1.900000 |  | 2021-01-19 21:16:25 | 2021-03-24 21:07:50 | 2021-01-19 21:16:25 | 2021-01-20 12:25:17 | 2021-03-11 19:40:37 |  | N | [6 empty] | 2375279106 | Hardware installation | MC |  | 2020-12-22 18:36:20 | 56A0A8L |  | Normal task | 2021-03-11 19:40:37 |  | 2021-01-20 12:25:17
3002041177006 | 77_10616 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_10616 | 77_10616 |  | ISDP RolloutPlan | 13 | 13 | 12 | 1 | Pre-installation QC Plan | N |  |  | V1.900000 |  | 2021-01-20 15:51:57 | 2021-02-01 16:46:46 | 2021-01-20 15:51:57 | 2021-01-21 10:30:09 | 2021-02-01 16:49:24 |  | N | [6 empty] | 2649497106 | Hardware installation | MC |  | 2021-01-20 08:45:25 | 56A0A8L |  | Owner changed | 2021-02-01 16:49:24 |  | 2021-01-21 10:30:09
3002041321006 | 77_11299 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_11299 | 77_11299 |  | ISDP RolloutPlan | 13 | 13 | 5 | 8 | Pre-installation QC Plan | N |  |  | V1.900000 |  | 2021-01-23 11:09:54 | 2021-02-06 17:41:27 | 2021-01-23 11:09:54 | 2021-01-23 15:48:11 | 2021-02-02 14:31:36 |  | N | [6 empty] | 2420676106 | Hardware installation | MO |  | 2021-01-22 10:28:30 | 56A0A8L |  | Normal task | 2021-02-02 14:31:36 |  | 2021-01-23 15:48:11
3002042539006 | 77_05077 |  |  |  |  | QC-TE Operation quality | Pass With Minor Issues |  | PL_77_5077 | 77_5077 |  | ISDP RolloutPlan | 13 | 13 | 12 | 1 | Pre-installation QC Plan | N |  |  | V1.900000 |  | 2021-02-17 15:49:11 | 2021-04-22 17:15:52 | 2021-02-17 15:49:11 | 2021-02-17 16:18:02 | 2021-04-22 17:15:52 |  | N | [6 empty] | 2319631106 | Hardware installation | MC |  | 2021-02-16 14:40:44 | 56A0A8L |  | Normal task | 2021-02-26 17:42:13 |  | 2021-02-17 16:18:02
3002043275006 | 77_03840 |  |  |  |  | QC-TE Operation quality | Pass With Minor Issues |  | PL_77_3840 | 77_3840 |  | ISDP RolloutPlan | 13 | 13 | 12 | 1 | Pre-installation QC Plan | N |  |  | V1.900000 |  | 2021-03-02 19:20:18 | 2021-04-22 17:17:24 | 2021-03-02 19:20:18 | 2021-03-03 10:45:37 | 2021-04-22 17:17:24 |  | N | [6 empty] | 2487251106 | Hardware installation | MO |  | 2021-03-01 11:08:41 | 56A0A8L |  | Normal task | 2021-03-16 16:20:16 |  | 2021-03-03 10:45:37
3002043286006 | 77_02892 |  |  |  |  | QC-TE Operation quality | Pass With Minor Issues |  | PL_77_2892 | 77_2892 |  | ISDP RolloutPlan | 13 | 13 | 12 | 1 | Pre-installation QC Plan | N |  |  | V1.900000 |  | 2021-03-01 12:03:49 | 2021-03-17 07:26:11 | 2021-03-01 12:03:49 | 2021-03-01 14:59:02 | 2021-03-17 07:26:11 |  | N | [6 empty] | 2535457106 | Hardware installation | MC |  | 2021-03-01 11:16:11 | 56A0A8L |  | Normal task | 2021-03-03 10:54:56 |  | 2021-03-01 14:59:02
3002043992006 | 77_05591 |  |  |  |  | QC-TE Operation quality | Pass With Minor Issues |  | PL_77_5591 | 77_5591 |  | ISDP RolloutPlan | 13 | 13 | 12 | 1 | Pre-installation QC Plan | N |  |  | V1.900000 |  | 2021-03-18 11:18:43 | 2021-04-22 17:16:43 | 2021-03-18 11:18:43 | 2021-03-19 20:19:10 | 2021-04-22 17:16:43 |  | N | [6 empty] | 2407225106 | Hardware installation | MO |  | 2021-03-15 13:11:11 | 56A0A8L |  | Normal task | 2021-04-06 14:30:18 |  | 2021-03-19 20:19:10
3002044386006 | 77_00242 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_242 | 77_242 |  | ISDP RolloutPlan | 8 | 8 | 7 | 0 | Site Cleanup QC plan | N |  |  | V1.300000 |  | 2021-04-25 09:41:38 | 2021-05-18 14:28:24 | 2021-04-25 09:41:38 | 2021-04-30 11:16:09 | 2021-05-19 16:59:11 |  | N | [6 empty] | 2637364106 | Site Cleanup | MC |  | 2021-03-22 13:09:39 | 56A0A8L |  | Normal task | 2021-05-19 16:59:11 |  | 2021-04-30 11:16:09
3002044387006 | 77_18108 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_18108 | 77_18108 |  | ISDP RolloutPlan | 8 | 8 | 5 | 0 | Site Cleanup QC plan | N |  |  | V1.100000 |  | 2021-03-22 14:00:31 | 2021-03-22 15:27:02 | 2021-03-22 14:00:31 | 2021-03-22 19:46:45 | 2021-03-22 19:56:38 |  | N | [6 empty] | 2679358106 | Site Cleanup | MO |  | 2021-03-22 13:15:23 | 56A0A8L |  | Normal task | 2021-03-22 19:56:38 |  | 2021-03-22 19:46:45
3002045081006 | 77_10210 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_10210 | 77_10210 |  | ISDP RolloutPlan | 17 | 17 | 16 | 0 | Site Cleanup QC plan | N |  |  | V1.300000 |  | 2021-04-15 13:02:25 | 2021-06-08 15:07:59 | 2021-04-15 13:02:25 | 2021-04-15 18:40:52 | 2021-06-08 15:44:24 |  | N | [6 empty] | 2326218106 | Hardware installation | MC |  | 2021-03-31 19:22:20 | 56A0A8L |  | Owner changed | 2021-06-08 15:44:24 |  | 2021-04-15 18:40:52
3002045131006 | 77_11555 |  |  |  |  | QC-TE Operation quality | Pass With Minor Issues |  | PL_77_11555 | 77_11555 |  | ISDP RolloutPlan | 8 | 8 | 6 | 2 | Equipment acceptance | N |  |  | V2.600000 |  | 2021-04-05 10:51:04 | 2021-07-19 16:10:30 | 2021-04-05 10:51:04 | 2021-04-05 23:11:08 | 2021-07-19 16:10:30 |  | N | [6 empty] | 3306221106 | Equipment Acceptance | MO |  | 2021-04-02 00:11:47 | 56A0A8L |  | Normal task | 2021-04-09 09:10:37 |  | 2021-04-05 23:11:08
3002045604006 | 77_00249 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_249 | 77_249 |  | ISDP RolloutPlan | 19 | 16 | 0 | 0 | Site Cleanup QC plan | N |  |  | V1.300000 |  | 2021-07-13 10:14:34 | 2021-07-13 11:50:32 | 2021-07-13 10:14:34 |  |  |  | N | [6 empty] | 2637548106 | Site Cleanup | MC |  | 2021-04-06 16:53:13 | 56A0A8L |  | Owner changed
3002049442006 | 77_05469 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_5469 | 77_5469 |  | ISDP RolloutPlan | 57 | 49 | 44 | 4 | Moscow SWAP QC Plan | Y | 2021-07-08 17:37:19 | 2021-07-08 17:37:38 | V3.200000 |  | 2021-07-08 15:07:54 | 2021-07-14 13:21:26 | 2021-07-08 15:07:54 | 2021-07-08 17:29:55 | 2021-07-09 17:40:03 |  | N | [6 empty] | 2454355106 | Smart QC task(installation) | MC |  | 2021-05-19 08:44:39 | 56A0A8L |  | Owner changed | 2021-07-09 17:40:03 |  | 2021-07-08 17:29:55
3002050103006 | 77_12081 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_12081 | 77_12081 |  | ISDP RolloutPlan | 57 | 56 | 46 | 10 | Moscow SWAP QC Plan | Y | 2021-05-26 16:52:49 | 2021-05-26 16:52:49 | V3.200000 |  | 2021-05-26 16:45:50 | 2021-06-07 09:09:47 | 2021-05-26 16:45:50 | 2021-05-26 16:52:49 | 2021-06-21 15:18:22 |  | N | [6 empty] | 2291625106 | Smart QC task(installation) | MC |  | 2021-05-24 12:27:56 | 56A0A8L |  | Normal task | 2021-06-21 15:18:20 |  | 2021-05-26 19:23:04
3002051258006 | 77_05632 |  |  |  |  | QC-TE Operation quality | Pass With Minor Issues |  | PL_77_5632 | 77_5632 |  | ISDP RolloutPlan | 13 | 13 | 10 | 3 | Pre-installation QC Plan | N |  |  | V2.100000 |  | 2021-06-03 10:32:39 | 2021-06-20 14:46:43 | 2021-06-03 10:32:39 | 2021-06-03 14:14:44 | 2021-06-20 14:46:43 |  | N | [6 empty] | 2457882106 | Hardware installation | MO |  | 2021-06-02 19:08:28 | 56A0A8L |  | Normal task | 2021-06-14 18:25:21 |  | 2021-06-03 14:14:44
3002051554006 | 77_20523 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_20523 | 77_20523 |  | ISDP RolloutPlan | 13 | 13 | 5 | 8 | Site Cleanup QC plan | N |  |  | V1.900000 |  | 2021-06-05 18:37:31 | 2021-07-18 19:41:42 | 2021-06-05 18:37:31 | 2021-06-17 13:56:29 | 2021-06-17 14:36:28 |  | N | [6 empty] | 2523470106 | Site Cleanup | MO |  | 2021-06-04 17:02:21 | 56A0A8L |  | Owner changed | 2021-06-17 14:36:26 |  | 2021-06-17 13:56:29
3002052956006 | 77_20163 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_20163 | 77_20163 |  | ISDP RolloutPlan | 11 | 11 | 10 | 0 | Site Cleanup QC plan | N |  |  | V1.900000 |  | 2021-07-02 16:11:10 | 2021-07-02 18:59:14 | 2021-07-02 16:11:10 | 2021-07-06 10:44:59 | 2021-07-06 11:24:45 |  | N | [6 empty] | 2632170106 | Site Cleanup | MC |  | 2021-06-20 11:13:06 | 56A0A8L |  | Owner changed | 2021-07-06 11:24:45 |  | 2021-07-06 10:44:59
3002053228006 | 77_06265 |  |  |  |  | QC-TE Operation quality | Pass With Minor Issues |  | PL_77_6265 | 77_6265 |  | ISDP RolloutPlan | 57 | 57 | 55 | 2 | Moscow SWAP QC Plan | Y | 2021-06-29 11:26:02 | 2021-06-29 11:26:19 | V3.200000 |  | 2021-06-29 11:26:01 | 2021-07-05 09:53:35 | 2021-06-29 11:26:01 | 2021-06-29 11:26:02 | 2021-07-05 09:53:35 |  | N | [6 empty] | 2462518106 | Smart QC task(installation) | MO |  | 2021-06-22 10:22:15 | 56A0A8L |  | Normal task | 2021-06-30 18:19:31 |  | 2021-06-29 12:48:20
3002053462006 | 77_10981 |  |  |  |  | QC-TE Operation quality | Pass With Minor Issues |  | PL_77_10981 | 77_10981 |  | ISDP RolloutPlan | 13 | 13 | 10 | 3 | Pre-installation QC Plan | N |  |  | V2.100000 |  | 2021-06-26 09:09:59 | 2021-07-07 20:28:50 | 2021-06-26 09:09:59 | 2021-06-26 11:37:30 | 2021-07-07 20:28:50 |  | N | [6 empty] | 2607054106 | Hardware installation | MO |  | 2021-06-23 14:45:02 | 56A0A8L |  | Normal task | 2021-07-07 13:22:53 |  | 2021-06-26 11:37:30
3002053488006 | 77_11716 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_11716 | 77_11716 |  | ISDP RolloutPlan | 60 | 60 | 51 | 2 | Moscow SWAP QC Plan | Y | 2021-07-19 13:24:54 | 2021-07-19 15:14:22 | V3.500000 |  | 2021-07-02 17:37:39 | 2021-07-20 12:38:19 | 2021-07-02 17:37:39 | 2021-07-04 10:28:27 | 2021-07-20 12:53:47 |  | N | [6 empty] | 2288900106 | Smart QC task(installation) | MO |  | 2021-06-23 17:40:02 | 56A0A8L |  | Normal task | 2021-07-20 12:53:47 |  | 2021-07-04 10:28:27
3002053999006 | 77_10845 |  |  |  |  | QC-TE Operation quality | Pass With Minor Issues |  | PL_77_10845 | 77_10845 |  | ISDP RolloutPlan | 60 | 60 | 58 | 2 | Moscow SWAP QC Plan | Y | 2021-06-30 14:25:55 | 2021-06-30 14:26:15 | V3.600000 |  | 2021-06-30 10:51:54 | 2021-07-05 09:52:36 | 2021-06-30 10:51:54 | 2021-06-30 12:48:18 | 2021-07-05 09:52:36 |  | N | [6 empty] | 2603143106 | Smart QC task(installation) | MO |  | 2021-06-28 09:41:24 | 56A0A8L |  | Normal task | 2021-06-30 19:54:46 |  | 2021-06-30 12:48:18
3002054144006 | 77_20175 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_20175 | 77_20175 |  | ISDP RolloutPlan | 38 | 30 | 10 | 0 | Site Cleanup QC plan | N |  |  | V2.600000 |  | 2021-07-16 22:15:26 | 2021-07-17 03:47:12 | 2021-07-16 22:15:26 | 2021-07-17 00:03:21 | 2021-07-17 00:03:21 |  | N | [6 empty] | 2632915106 | Site Cleanup | MC |  | 2021-06-29 12:01:41 | 56A0A8L |  | Normal task | 2021-07-17 00:03:21 |  | 2021-07-17 00:03:21
3002054182006 | 77_12012 |  |  |  |  | QC-TE Operation quality | Pass With Minor Issues |  | PL_77_12012 | 77_12012 |  | ISDP RolloutPlan | 11 | 11 | 10 | 1 | Lamp Pole Painting | N |  |  | V1.200000 |  | 2021-07-05 09:57:44 | 2021-07-05 12:22:39 | 2021-07-05 09:57:44 | 2021-07-05 11:53:20 | 2021-07-05 12:22:39 |  | N | [6 empty] | 11750808106 | Lamp Pole Painting | MC |  | 2021-06-29 17:39:55 | 56A0A8L |  | Normal task | 2021-07-05 11:55:41 |  | 2021-07-05 11:53:20
3002054370006 | 77_14192 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_14192 | 77_14192 |  | ISDP RolloutPlan | 38 | 36 | 31 | 3 | Site Cleanup QC plan | N |  |  | V2.600000 |  | 2021-07-01 15:59:36 | 2021-07-01 19:07:13 | 2021-07-01 15:59:36 | 2021-07-01 18:54:33 | 2021-07-01 19:08:49 |  | N | [6 empty] | 2351970106 | Site Cleanup | MC |  | 2021-06-30 22:57:00 | 56A0A8L |  | Normal task | 2021-07-01 19:08:48 |  | 2021-07-01 18:54:33
3002054461006 | 77_13171 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_13171 | 77_13171 |  | ISDP RolloutPlan | 47 | 45 | 43 | 2 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-09 10:44:56 | 2021-07-18 15:19:56 | 2021-07-09 10:44:56 | 2021-07-09 20:06:39 | 2021-07-16 16:08:05 |  | N | [6 empty] | 2248324106 | Smart QC task(installation) | MC |  | 2021-07-01 16:07:54 | 56A0A8L |  | Owner changed | 2021-07-16 16:08:05 |  | 2021-07-09 20:06:39
3002054515006 | 77_04055 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_4055 | 77_4055 |  | ISDP RolloutPlan | 38 | 30 | 0 | 1 | Site Cleanup QC plan | N |  |  | V2.600000 |  | 2021-07-09 12:31:42 | 2021-07-13 13:34:44 | 2021-07-09 12:31:42 | 2021-07-15 11:40:13 | 2021-07-15 11:40:13 |  | N | [6 empty] | 12180609106 | Site Cleanup | MC |  | 2021-07-02 10:34:48 | 56A0A8L |  | Normal task | 2021-07-15 11:40:13 |  | 2021-07-15 11:40:13
3002054551006 | 77_12628 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_12628 | 77_12628 |  | ISDP RolloutPlan | 40 | 40 | 38 | 1 | Site Cleanup QC plan | N |  |  | V2.600000 |  | 2021-07-03 10:00:02 | 2021-07-03 14:55:37 | 2021-07-03 10:00:02 | 2021-07-03 12:24:12 | 2021-07-03 17:16:41 |  | N | [6 empty] | 2611219106 | Site Cleanup | MC |  | 2021-07-02 14:48:39 | 56A0A8L |  | Normal task | 2021-07-03 17:16:41 |  | 2021-07-03 12:24:12
3002054614006 | 77_20307 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_20307 | 77_20307 |  | ISDP RolloutPlan | 38 | 38 | 36 | 1 | Site Cleanup QC plan | N |  |  | V2.600000 |  | 2021-07-09 11:08:02 | 2021-07-09 15:37:13 | 2021-07-09 11:08:02 | 2021-07-09 15:29:03 | 2021-07-09 15:39:33 |  | N | [6 empty] | 2578959106 | Site Cleanup | MC |  | 2021-07-02 16:12:18 | 56A0A8L |  | Normal task | 2021-07-09 15:39:33 |  | 2021-07-09 15:29:03
3002054644006 | 77_04033 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_4033 | 77_4033 |  | ISDP RolloutPlan | 38 | 33 | 2 | 3 | Site Cleanup QC plan | N |  |  | V2.600000 |  | 2021-07-07 18:36:14 | 2021-07-07 18:47:42 | 2021-07-07 18:36:14 | 2021-07-08 17:04:12 | 2021-07-08 17:15:44 |  | N | [6 empty] | 2449186106 | Site Cleanup | MC |  | 2021-07-03 10:20:47 | 56A0A8L |  | Normal task | 2021-07-08 17:15:42 |  | 2021-07-08 17:04:12
3002054656006 | 77_15169 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_15169 | 77_15169 |  | ISDP RolloutPlan | 38 | 35 | 29 | 6 | Site Cleanup QC plan | N |  |  | V2.600000 |  | 2021-07-03 17:10:20 | 2021-07-12 09:42:39 | 2021-07-03 17:10:20 | 2021-07-03 17:13:17 | 2021-07-05 07:06:21 |  | N | [6 empty] | 12185379106 | Site Cleanup | MO |  | 2021-07-03 15:19:53 | 56A0A8L |  | Normal task | 2021-07-05 07:06:19 |  | 2021-07-03 17:13:17
3002055309006 | 77_01214 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_1214 | 77_1214 |  | ISDP RolloutPlan | 60 | 15 | 9 | 3 | Moscow SWAP QC Plan | N |  |  | V3.600000 |  | 2021-07-16 12:15:28 | 2021-07-19 18:40:15 | 2021-07-16 12:15:28 | 2021-07-16 14:52:19 | 2021-07-16 18:44:19 |  | N | [6 empty] | 2292400106 | Smart QC task(installation) | MC |  | 2021-07-08 15:22:03 | 56A0A8L |  | Normal task | 2021-07-16 18:44:19 |  | 2021-07-16 14:52:19
3002055391006 | 77_14063 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_14063 | 77_14063 |  | ISDP RolloutPlan | 47 | 45 | 13 | 7 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-10 10:38:26 | 2021-07-20 10:04:06 | 2021-07-10 10:38:26 | 2021-07-10 13:15:17 | 2021-07-13 15:43:43 |  | N | [6 empty] | 2348627106 | Smart QC task(installation) | MC |  | 2021-07-09 13:48:29 | 56A0A8L |  | Normal task | 2021-07-13 15:45:10 |  | 2021-07-10 13:15:17
3002055401006 | 77_14063 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_14063 | 77_14063 |  | ISDP RolloutPlan | 11 | 11 | 3 | 0 | Lamp Pole Painting | N |  |  | V1.200000 |  | 2021-07-10 14:04:42 | 2021-07-17 15:29:58 | 2021-07-10 14:04:42 | 2021-07-10 14:54:13 | 2021-07-13 15:38:31 |  | N | [6 empty] | 11749945106 | Lamp Pole Painting | MC |  | 2021-07-09 13:52:24 | 56A0A8L |  | Normal task | 2021-07-13 15:38:31 |  | 2021-07-10 14:54:13
3002055403006 | 77_16678 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_16678 | 77_16678 |  | ISDP RolloutPlan | 11 | 11 | 0 | 0 | Lamp Pole Painting | N |  |  | V1.200000 |  | 2021-07-14 12:32:06 | 2021-07-14 12:32:10 | 2021-07-14 12:32:06 |  |  |  | N | [6 empty] | 11754190106 | Lamp Pole Painting | MC |  | 2021-07-09 15:01:40 | 56A0A8L |  | Normal task
3002055433006 | 77_01398 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_1398 | 77_1398 |  | ISDP RolloutPlan | 60 | 20 | 11 | 8 | Moscow SWAP QC Plan | N |  |  | V3.600000 |  | 2021-07-13 12:57:56 | 2021-07-17 18:14:35 | 2021-07-13 12:57:56 | 2021-07-16 11:21:24 | 2021-07-18 10:11:51 |  | N | [6 empty] | 2346601106 | Smart QC task(installation) | MC |  | 2021-07-09 16:10:09 | 56A0A8L |  | Normal task | 2021-07-18 10:13:21 |  | 2021-07-16 11:21:24
3118057006 | 77_11777 |  |  |  |  | QC-EHS | Pass With Minor Issues |  | PL_77_11777 | 77_11777 |  | ISDP MOBILE | 11 | 11 | 10 | 1 | EHS daily check | Y | 2021-07-17 14:15:11 | 2021-07-17 14:15:11 | V2.900000 |  | 2021-07-17 14:10:27 | 2021-07-20 10:42:02 | 2021-07-17 14:10:27 | 2021-07-17 14:12:52 | 2021-07-20 10:42:02 |  | N | [8 empty] | MO |  | 2021-07-17 14:10:04 | 56A0A8L |  | Normal task | 2021-07-17 14:23:03 |  | 2021-07-17 14:12:52
3120077006 | 77_02341 |  |  |  |  | QC-EHS | Pass With Minor Issues |  | PL_77_2341 | 77_2341 |  | ISDP MOBILE | 11 | 11 | 10 | 1 | EHS daily check | Y | 2021-07-19 11:47:53 | 2021-07-19 11:48:09 | V2.900000 |  | 2021-07-19 11:47:51 | 2021-07-19 18:08:54 | 2021-07-19 11:47:51 | 2021-07-19 11:47:53 | 2021-07-19 18:08:54 |  | N | [8 empty] | MC |  | 2021-07-19 11:45:53 | 56A0A8L |  | Normal task | 2021-07-19 12:50:57 |  | 2021-07-19 12:18:59
3002054496006 | 77_10153 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_10153 | 77_10153 |  | ISDP RolloutPlan | 38 | 1 | 0 | 0 | Site Cleanup QC plan | N |  |  | V2.600000 |  | 2021-07-02 19:28:29 | 2021-07-02 20:00:39 | 2021-07-02 19:28:29 |  |  |  | N | [6 empty] | 2282199106 | Site Cleanup | MC |  | 2021-07-01 22:59:33 | 56A0A8L |  | Normal task
3002039947006 | 77_06188 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_6188 | 77_6188 |  | ISDP RolloutPlan | 13 | 13 | 11 | 2 | Pre-installation QC Plan | N |  |  | V1.900000 |  | 2020-12-20 10:51:38 | 2021-03-30 16:49:27 | 2020-12-20 10:51:38 | 2020-12-22 12:33:23 | 2021-03-12 13:57:24 |  | N | [6 empty] | 2601388106 | Hardware installation | MC |  | 2020-12-16 09:08:14 | 56A0A8L |  | Normal task | 2021-03-12 13:57:24 |  | 2020-12-22 12:33:23
3002041395006 | 77_00866 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_866 | 77_866 |  | ISDP RolloutPlan | 13 | 13 | 10 | 3 | Pre-installation QC Plan | N |  |  | V1.900000 |  | 2021-01-27 10:08:19 | 2021-03-26 11:47:59 | 2021-01-27 10:08:19 | 2021-01-27 13:52:36 | 2021-02-02 11:17:22 |  | N | [6 empty] | 2692639106 | Hardware installation | MC |  | 2021-01-25 11:53:12 | 56A0A8L |  | Owner changed | 2021-02-02 11:17:22 |  | 2021-01-27 13:52:36
3002042792006 | 77_06194 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_6194 | 77_6194 |  | ISDP RolloutPlan | 13 | 9 | 7 | 2 | Pre-installation QC Plan | N |  |  | V1.900000 |  | 2021-02-19 11:42:18 | 2021-03-17 17:29:24 | 2021-02-19 11:42:18 | 2021-02-19 14:57:52 | 2021-03-05 13:07:29 |  | N | [6 empty] | 2601664106 | Hardware installation | MC |  | 2021-02-19 10:23:01 | 56A0A8L |  | Owner changed | 2021-03-05 13:07:29 |  | 2021-02-19 14:57:52
3002044761006 | 77_04489 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_4489 | 77_4489 |  | ISDP RolloutPlan | 13 | 13 | 3 | 10 | Pre-installation QC Plan | N |  |  | V1.900000 |  | 2021-04-17 12:28:48 | 2021-06-06 18:46:19 | 2021-04-17 12:28:48 | 2021-04-18 16:27:40 | 2021-06-06 15:58:59 |  | N | [6 empty] | 2542150106 | Hardware installation | MC |  | 2021-03-26 09:36:59 | 56A0A8L |  | Owner changed | 2021-06-06 15:58:58 |  | 2021-04-18 16:27:40
3002048217006 | 77_06190 |  |  |  |  | QC-TE Operation quality | Pass With Minor Issues |  | PL_77_6190 | 77_6190 |  | ISDP RolloutPlan | 57 | 57 | 53 | 4 | Moscow SWAP QC Plan | Y | 2021-05-25 13:17:46 | 2021-05-25 13:18:03 | V3.200000 |  | 2021-05-19 20:54:27 | 2021-07-06 13:11:45 | 2021-05-19 20:54:27 | 2021-05-21 15:25:48 | 2021-07-06 13:11:45 |  | N | [6 empty] | 2601476106 | Smart QC task(installation) | MC |  | 2021-05-11 09:37:43 | 56A0A8L |  | Owner changed | 2021-06-23 17:02:43 |  | 2021-05-21 15:25:48
3002048427006 | 77_00455 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_455 | 77_455 |  | ISDP RolloutPlan | 9 | 9 | 8 | 0 | Site Cleanup QC plan | N |  |  | V1.500000 |  | 2021-05-13 11:26:19 | 2021-05-13 13:08:52 | 2021-05-13 11:26:19 | 2021-05-13 12:36:44 | 2021-05-13 12:38:35 |  | N | [6 empty] | 11789200106 | Site Cleanup | MC |  | 2021-05-13 09:38:31 | 56A0A8L |  | Owner changed | 2021-05-13 12:38:35 |  | 2021-05-13 12:36:44
3002049934006 | 77_06188 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_6188 | 77_6188 |  | ISDP RolloutPlan | 9 | 6 | 0 | 2 | Site Cleanup QC plan | N |  |  | V1.900000 |  | 2021-06-03 15:23:47 | 2021-06-08 14:13:29 | 2021-06-03 15:23:47 | 2021-06-22 17:17:31 | 2021-06-22 17:44:08 |  | N | [6 empty] | 2601391106 | Site Cleanup | MC |  | 2021-05-22 08:07:23 | 56A0A8L |  | Normal task | 2021-06-22 17:44:07 |  | 2021-06-22 17:17:31
2805695006 | 77_17667_RD |  |  |  |  | QC-EHS | Pass With Minor Issues |  | PL_77_17667 | 77_17667 |  | ISDP MOBILE | 10 | 10 | 9 | 1 | EHS check | N |  |  | V2.400000 |  | 2021-04-21 09:34:35 | 2021-07-19 12:12:50 | 2021-04-21 09:34:35 | 2021-04-21 11:32:49 | 2021-04-21 11:36:14 |  | N | [8 empty] | MC |  | 2021-04-21 09:31:29 | 56A0A8L |  | Normal task | 2021-04-21 11:36:13 |  | 2021-04-21 11:32:49
3002052662006 | 77_77063 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_77063 | 77_77063 |  | ISDP RolloutPlan | 53 | 51 | 46 | 0 | Metro MTS QC Plan | Y | 2021-07-13 02:12:01 | 2021-07-13 02:12:20 | V1.600000 |  | 2021-07-08 00:43:07 | 2021-07-14 03:29:27 | 2021-07-08 00:43:07 | 2021-07-13 02:12:01 | 2021-07-14 03:46:21 |  | N | [6 empty] | 3367507106 | Smart QC task(installation) | Metro |  | 2021-06-16 20:28:12 | 56A0A8L |  | Normal task | 2021-07-14 03:46:21 |  | 2021-07-13 02:50:18
3002054762006 | 77_12601 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_12601 | 77_12601 |  | ISDP RolloutPlan | 4 | 4 | 0 | 0 | Metro Equipment acceptance | N |  |  | V1.400000 |  | 2021-07-16 01:32:36 | 2021-07-20 03:52:07 | 2021-07-16 01:32:36 |  |  |  | N | [6 empty] | 3364155106 | Equipment Acceptance | Metro |  | 2021-07-05 12:09:34 | 56A0A8L |  | Normal task
3002054781006 | 77_12601 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_12601 | 77_12601 |  | ISDP RolloutPlan | 53 | 50 | 31 | 1 | Metro MTS QC Plan | Y | 2021-07-20 03:23:04 | 2021-07-20 03:23:05 | V1.600000 |  | 2021-07-15 05:15:42 | 2021-07-20 04:02:56 | 2021-07-15 05:15:42 | 2021-07-16 04:29:13 | 2021-07-20 04:58:54 |  | N | [6 empty] | 3364157106 | Smart QC task(installation) | Metro |  | 2021-07-05 12:10:04 | 56A0A8L |  | Normal task | 2021-07-20 04:58:54 |  | 2021-07-16 04:29:13
3002040687006 | 77_16924 |  |  |  |  | QC-TE Operation quality | Pass With Minor Issues |  | PL_77_16924 | 77_16924 |  | ISDP RolloutPlan | 13 | 13 | 12 | 1 | Pre-installation QC Plan | N |  |  | V1.900000 |  | 2020-12-25 08:18:28 | 2021-04-23 06:49:53 | 2020-12-25 08:18:28 | 2020-12-28 13:59:08 | 2021-04-23 06:49:53 |  | N | [6 empty] | 11331578106 | SWAP(On Air) | MC |  | 2020-12-25 07:34:20 | 56A0A8L |  | Owner changed | 2021-01-25 13:40:32 |  | 2020-12-28 13:59:08
3002042383006 | 77_16430 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_16430 | 77_16430 |  | ISDP RolloutPlan | 57 | 57 | 52 | 5 | Moscow SWAP QC Plan | Y | 2021-03-05 11:50:09 | 2021-03-05 11:50:09 | V3.100000 |  | 2021-03-05 11:01:44 | 2021-07-09 14:38:35 | 2021-03-05 11:01:44 | 2021-03-05 11:50:09 | 2021-03-05 14:40:00 |  | N | [6 empty] | 2307604106 | Smart QC task(installation) | MC |  | 2021-02-11 08:59:31 | 56A0A8L |  | Owner changed | 2021-03-05 14:40:00 |  | 2021-03-05 13:34:33
3002042560006 | 77_16945 |  |  |  |  | QC-TE Operation quality | Pass With Minor Issues |  | PL_77_16945 | 77_16945 |  | ISDP RolloutPlan | 57 | 57 | 56 | 1 | Moscow SWAP QC Plan | Y | 2021-02-19 13:05:34 | 2021-02-19 13:05:34 | V3.100000 |  | 2021-02-19 12:43:54 | 2021-07-07 09:31:25 | 2021-02-19 12:43:54 | 2021-02-19 13:05:34 | 2021-07-07 09:31:25 |  | N | [6 empty] | 2673669106 | Smart QC task(installation) | MC |  | 2021-02-16 09:12:00 | 56A0A8L |  | Normal task | 2021-03-18 13:33:42 |  | 2021-02-19 14:41:38
3002042562006 | 77_16945 |  |  |  |  | QC-TE Operation quality | Pass With Minor Issues |  | PL_77_16945 | 77_16945 |  | ISDP RolloutPlan | 13 | 13 | 12 | 1 | Pre-installation QC Plan | N |  |  | V1.900000 |  | 2021-02-18 13:25:14 | 2021-07-07 09:46:14 | 2021-02-18 13:25:14 | 2021-02-19 15:42:47 | 2021-07-07 09:46:14 |  | N | [6 empty] | 2673673106 | Hardware installation | MC |  | 2021-02-16 09:16:52 | 56A0A8L |  | Normal task | 2021-02-20 15:25:51 |  | 2021-02-19 15:42:47
3002047770006 | 77_10221 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_10221 | 77_10221 |  | ISDP RolloutPlan | 8 | 8 | 7 | 0 | Site Cleanup QC plan | N |  |  | V1.400000 |  | 2021-05-05 10:38:28 | 2021-05-05 10:47:06 | 2021-05-05 10:38:28 | 2021-05-05 10:47:25 | 2021-05-05 21:33:07 |  | N | [6 empty] | 2326805106 | Site Cleanup | MC |  | 2021-05-04 17:02:50 | 56A0A8L |  | Normal task | 2021-05-05 21:33:07 |  | 2021-05-05 10:47:25
3002053219006 | 77_17095 |  |  |  |  | QC-TE Operation quality | Pass With Minor Issues |  | PL_77_17095 | 77_17095 |  | ISDP RolloutPlan | 13 | 13 | 12 | 1 | Pre-installation QC Plan | N |  |  | V2.100000 |  | 2021-06-29 07:13:20 | 2021-07-09 10:10:48 | 2021-06-29 07:13:20 | 2021-06-29 11:09:54 | 2021-07-09 10:10:48 |  | N | [6 empty] | 2436028106 | Hardware installation | MC |  | 2021-06-22 06:59:05 | 56A0A8L |  | Normal task | 2021-06-29 17:00:12 |  | 2021-06-29 11:09:54
3002054696006 | 77_17041 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_17041 | 77_17041 |  | ISDP RolloutPlan | 38 | 38 | 0 | 0 | Site Cleanup QC plan | N |  |  | V2.600000 |  | 2021-07-05 09:58:33 | 2021-07-05 10:46:28 | 2021-07-05 09:58:33 |  |  |  | N | [6 empty] | 12185115106 | Site Cleanup | MO |  | 2021-07-05 08:57:24 | 56A0A8L |  | Normal task
3002055054006 | 77_04624 |  |  |  |  | QC-TE Operation quality | Pass With Minor Issues |  | PL_77_4624 | 77_4624 |  | ISDP RolloutPlan | 13 | 13 | 10 | 3 | Pre-installation QC Plan | N |  |  | V2.100000 |  | 2021-07-07 10:17:11 | 2021-07-16 19:14:16 | 2021-07-07 10:17:11 | 2021-07-07 19:16:46 | 2021-07-16 19:14:16 |  | N | [6 empty] | 2548246106 | Hardware installation | MO |  | 2021-07-07 10:00:41 | 56A0A8L |  | Normal task | 2021-07-15 17:00:06 |  | 2021-07-07 19:16:46
3302264827006 | 77_16483 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_16483 | 77_16483 |  | ISDP RolloutPlan | 13 | 9 | 0 | 0 | Pre-installation QC Plan | N |  |  | V2.1 |  | 2021-07-20 11:53:46 | 2021-07-20 12:48:10 | 2021-07-20 11:53:46 |  |  |  | N | [6 empty] | 2309850106 | Hardware installation | MC |  | 2021-07-19 10:07:26 | 56A0A8L |  | Normal task
3002048890006 | 77_16441 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_16441 | 77_16441 |  | ISDP RolloutPlan | 57 | 1 | 0 | 0 | Moscow SWAP QC Plan | N |  |  | V3.200000 |  | 2021-07-14 13:15:25 | 2021-07-14 14:11:25 | 2021-07-14 13:15:25 |  |  |  | N | [6 empty] | 2308234106 | Smart QC task(installation) | MC |  | 2021-05-17 12:19:56 | 56A0A8L |  | Normal task
3002055161006 | 77_16904 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_16904 | 77_16904 |  | ISDP RolloutPlan | 60 | 9 | 0 | 0 | Moscow SWAP QC Plan | N |  |  | V3.600000 |  | 2021-07-16 12:06:24 | 2021-07-16 13:08:44 | 2021-07-16 12:06:24 |  |  |  | N | [6 empty] | 2672103106 | Smart QC task(installation) | MC |  | 2021-07-07 15:04:44 | 56A0A8L |  | Normal task
3002054799006 | 77_03975 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_3975 | 77_3975 |  | ISDP RolloutPlan | 60 | 44 | 38 | 5 | Moscow SWAP QC Plan | Y | 2021-07-07 15:07:50 | 2021-07-07 15:08:07 | V3.600000 |  | 2021-07-07 15:07:49 | 2021-07-14 19:26:11 | 2021-07-07 15:07:49 | 2021-07-07 15:07:50 | 2021-07-14 19:52:00 |  | N | [6 empty] | 2491980106 | Smart QC task(installation) | MO |  | 2021-07-05 14:04:50 | 56A0A8L |  | Normal task | 2021-07-14 19:53:29 |  | 2021-07-08 16:41:09
3302261927006 | 77_06017 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_6017 | 77_6017 |  | ISDP RolloutPlan | 60 | 57 | 54 | 1 | Moscow SWAP QC Plan | Y | 2021-07-19 14:26:50 | 2021-07-20 10:10:33 | V3.6 |  | 2021-07-19 10:46:53 | 2021-07-20 12:54:34 | 2021-07-19 10:46:53 | 2021-07-19 11:49:25 | 2021-07-20 12:16:34 |  | N | [6 empty] | 2555060106 | Smart QC task(installation) | MO |  | 2021-07-12 13:52:22 | 56A0A8L |  | Owner changed | 2021-07-20 12:16:34 |  | 2021-07-19 11:49:25
3302263292006 | 77_05556 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_5556 | 77_5556 |  | ISDP RolloutPlan | 38 | 20 | 0 | 0 | Site Cleanup QC plan | N |  |  | V2.6 |  | 2021-07-15 12:32:15 | 2021-07-15 13:12:22 | 2021-07-15 12:32:15 |  |  |  | N | [6 empty] | 2504273106 | Site Cleanup | MO |  | 2021-07-15 10:36:16 | 56A0A8L |  | Normal task
3302264005006 | 77_03491 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_3491 | 77_3491 |  | ISDP RolloutPlan | 38 | 26 | 21 | 2 | Site Cleanup QC plan | N |  |  | V2.600000 |  | 2021-07-16 11:16:40 | 2021-07-16 14:55:26 | 2021-07-16 11:16:40 | 2021-07-16 16:56:35 | 2021-07-16 16:59:46 |  | N | [6 empty] | 13585948106 | Site Cleanup | MO |  | 2021-07-16 10:26:47 | 56A0A8L |  | Normal task | 2021-07-16 17:01:15 |  | 2021-07-16 16:56:35
3002040136006 | 77_11485 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_11485 | 77_11485 |  | ISDP RolloutPlan | 13 | 13 | 0 | 13 | Pre-installation QC Plan | N |  |  | V1.900000 |  | 2021-01-06 08:52:25 | 2021-02-10 12:38:45 | 2021-01-06 08:52:25 | 2021-01-11 16:20:41 | 2021-01-11 16:21:21 |  | N | [6 empty] | 11300259106 | Smart QC task(installation) | MO |  | 2020-12-17 12:51:09 | 56A0A8L |  | Normal task | 2021-01-11 16:21:21 |  | 2021-01-11 16:20:41
3002052002006 | 77_04231 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_4231 | 77_4231 |  | ISDP RolloutPlan | 9 | 9 | 8 | 0 | Site Cleanup QC plan | N |  |  | V1.900000 |  | 2021-06-09 19:41:21 | 2021-06-10 15:33:41 | 2021-06-09 19:41:21 | 2021-06-10 17:14:35 | 2021-06-10 17:14:59 |  | N | [6 empty] | 2493123106 | Site Cleanup | MC |  | 2021-06-09 13:12:31 | 56A0A8L |  | Normal task | 2021-06-10 17:14:59 |  | 2021-06-10 17:14:35
3002054958006 | 77_04641 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_4641 | 77_4641 |  | ISDP RolloutPlan | 60 | 52 | 16 | 26 | Moscow SWAP QC Plan | Y | 2021-07-20 12:48:24 | 2021-07-20 12:48:25 | V3.600000 |  | 2021-07-11 17:03:52 | 2021-07-20 12:48:25 | 2021-07-11 17:03:52 | 2021-07-11 18:17:30 | 2021-07-20 12:48:25 |  | N | [6 empty] | 2549224106 | Smart QC task(installation) | MO |  | 2021-07-06 14:03:22 | 56A0A8L |  | Normal task | 2021-07-20 09:44:32 |  | 2021-07-11 18:17:30
3002055003006 | 77_06214 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_6214 | 77_6214 |  | ISDP RolloutPlan | 60 | 60 | 52 | 3 | Moscow SWAP QC Plan | Y | 2021-07-15 14:55:43 | 2021-07-15 17:13:29 | V3.600000 |  | 2021-07-13 17:16:02 | 2021-07-16 20:06:49 | 2021-07-13 17:16:02 | 2021-07-14 17:48:24 | 2021-07-15 23:15:04 |  | N | [6 empty] | 2460327106 | Smart QC task(installation) | MO |  | 2021-07-06 14:06:54 | 56A0A8L |  | Normal task | 2021-07-15 23:15:04 |  | 2021-07-14 17:48:24
3002055384006 | 77_06368 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_6368 | 77_6368 |  | ISDP RolloutPlan | 13 | 10 | 8 | 0 | Pre-installation QC Plan | N |  |  | V2.100000 |  | 2021-07-16 10:34:09 | 2021-07-17 15:54:17 | 2021-07-16 10:34:09 | 2021-07-16 11:43:13 | 2021-07-16 11:43:25 |  | N | [6 empty] | 2415810106 | Hardware installation | MO |  | 2021-07-09 11:26:55 | 56A0A8L |  | Normal task | 2021-07-16 11:43:25 |  | 2021-07-16 11:43:13
3002055334006 | 77_06368 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_6368 | 77_6368 |  | ISDP RolloutPlan | 8 | 8 | 2 | 6 | Equipment acceptance | N |  |  | V2.600000 |  | 2021-07-16 19:56:24 | 2021-07-17 17:07:26 | 2021-07-16 19:56:24 | 2021-07-17 09:06:57 | 2021-07-17 09:09:03 |  | N | [6 empty] | 3313184106 | Equipment Acceptance | MO |  | 2021-07-09 11:28:45 | 56A0A8L |  | Normal task | 2021-07-17 09:10:33 |  | 2021-07-17 09:06:57
3302263013006 | 77_00693 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_693 | 77_693 |  | ISDP RolloutPlan | 8 | 1 | 0 | 0 | Equipment acceptance | N |  |  | V2.6 |  | 2021-07-20 10:50:04 | 2021-07-20 10:50:06 | 2021-07-20 10:50:04 |  |  |  | N | [6 empty] | 3311572106 | Equipment Acceptance | MO |  | 2021-07-14 21:03:28 | 56A0A8L |  | Normal task
3302263766006 | 77_06015 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_6015 | 77_6015 |  | ISDP RolloutPlan | 60 | 3 | 0 | 0 | Moscow SWAP QC Plan | N |  |  | V3.6 |  | 2021-07-20 11:18:46 | 2021-07-20 12:13:12 | 2021-07-20 11:18:46 |  |  |  | N | [6 empty] | 2555014106 | Smart QC task(installation) | MO |  | 2021-07-15 23:10:00 | 56A0A8L |  | Normal task
3002048242006 | 77_02512 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_2512 | 77_2512 |  | ISDP RolloutPlan | 9 | 9 | 8 | 0 | Site Cleanup QC plan | N |  |  | V1.500000 |  | 2021-05-12 13:12:47 | 2021-05-12 18:51:57 | 2021-05-12 13:12:47 | 2021-05-12 19:09:44 | 2021-05-31 13:22:11 |  | N | [6 empty] | 2393893106 | Site Cleanup | MO |  | 2021-05-11 15:38:02 | 56A0A8L |  | Normal task | 2021-05-31 13:22:11 |  | 2021-05-12 19:09:44
3002054531006 | 77_05581 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_5581 | 77_5581 |  | ISDP RolloutPlan | 38 | 38 | 23 | 0 | Site Cleanup QC plan | N |  |  | V2.600000 |  | 2021-07-10 13:32:50 | 2021-07-10 16:25:28 | 2021-07-10 13:32:50 | 2021-07-10 16:12:37 | 2021-07-10 16:15:08 |  | N | [6 empty] | 2456218106 | Site Cleanup | MO |  | 2021-07-02 08:42:52 | 56A0A8L |  | Normal task | 2021-07-10 16:15:08 |  | 2021-07-10 16:12:37
3302264965006 | 77_05330 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_5330 | 77_5330 |  | ISDP RolloutPlan | 13 | 6 | 0 | 0 | Pre-installation QC Plan | N |  |  | V2.1 |  | 2021-07-20 11:33:25 | 2021-07-20 12:52:03 | 2021-07-20 11:33:25 |  |  |  | N | [6 empty] | 2500151106 | Hardware installation | MC |  | 2021-07-19 14:38:55 | 56A0A8L |  | Normal task
3002050762006 | 77_13359 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_13359 | 77_13359 |  | ISDP RolloutPlan | 11 | 11 | 5 | 6 | Lamp Pole Painting | N |  |  | V1.100000 |  | 2021-06-03 14:20:18 | 2021-06-03 17:27:33 | 2021-06-03 14:20:18 | 2021-06-03 16:08:43 | 2021-06-03 16:29:54 |  | N | [6 empty] | 11749597106 | Lamp Pole Painting | MC |  | 2021-05-28 11:49:46 | 56A0A8L |  | Normal task | 2021-06-03 16:29:52 |  | 2021-06-03 16:08:43
3002052566006 | 77_05339 |  |  |  |  | QC-TE Operation quality | Pass With Minor Issues |  | PL_77_5339 | 77_5339 |  | ISDP RolloutPlan | 57 | 57 | 55 | 2 | Moscow SWAP QC Plan | Y | 2021-06-23 16:11:50 | 2021-06-23 16:12:10 | V3.200000 |  | 2021-06-22 18:33:47 | 2021-07-20 07:08:22 | 2021-06-22 18:33:47 | 2021-06-23 16:11:50 | 2021-07-20 07:08:22 |  | N | [6 empty] | 2499290106 | Smart QC task(installation) | MC |  | 2021-06-15 20:30:14 | 56A0A8L |  | Normal task | 2021-07-19 18:10:06 |  | 2021-06-24 18:17:31
3302261266006 | 77_06475 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_6475 | 77_6475 |  | ISDP RolloutPlan | 38 | 29 | 10 | 0 | Site Cleanup QC plan | N |  |  | V2.600000 |  | 2021-07-15 15:29:22 | 2021-07-15 15:29:28 | 2021-07-15 15:29:22 | 2021-07-16 06:47:28 | 2021-07-16 06:47:28 |  | N | [6 empty] | 13493148106 | Site Cleanup | MC |  | 2021-07-11 00:15:36 | 56A0A8L |  | Normal task | 2021-07-16 06:47:28 |  | 2021-07-16 06:47:28
3302261977006 | 77_16014 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_16014 | 77_16014 |  | ISDP RolloutPlan | 47 | 47 | 46 | 0 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-19 09:53:02 | 2021-07-19 19:53:09 | 2021-07-19 09:53:02 | 2021-07-19 13:56:50 | 2021-07-19 20:07:03 |  | N | [6 empty] | 2431768106 | Smart QC task(installation) | MC |  | 2021-07-12 16:21:39 | 56A0A8L |  | Normal task | 2021-07-19 20:07:03 |  | 2021-07-19 13:56:50
3302261979006 | 77_16142 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_16142 | 77_16142 |  | ISDP RolloutPlan | 47 | 17 | 2 | 0 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-20 07:42:30 | 2021-07-20 12:45:58 | 2021-07-20 07:42:30 |  |  |  | N | [6 empty] | 2387885106 | Smart QC task(installation) | MC |  | 2021-07-12 16:22:04 | 56A0A8L |  | Normal task
3302262004006 | 77_17714 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_17714 | 77_17714 |  | ISDP RolloutPlan | 47 | 22 | 20 | 1 | Poles QC plan (ОДН) | N |  |  | V5.100000 |  | 2021-07-19 09:11:13 | 2021-07-20 12:11:59 | 2021-07-19 09:11:13 | 2021-07-19 13:34:06 | 2021-07-20 11:51:29 |  | N | [6 empty] | 2360133106 | Smart QC task(installation) | MC |  | 2021-07-12 16:22:21 | 56A0A8L |  | Normal task | 2021-07-20 11:51:29 |  | 2021-07-19 13:34:06
3302264085006 | 77_02081 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_2081 | 77_2081 |  | ISDP RolloutPlan | 38 | 6 | 0 | 0 | Site Cleanup QC plan | N |  |  | V2.6 |  | 2021-07-16 16:32:12 | 2021-07-20 09:37:13 | 2021-07-16 16:32:08 |  |  |  | N | [6 empty] | 2270303106 | Site Cleanup | MC |  | 2021-07-16 16:26:09 | 56A0A8L |  | Normal task
3302265328006 | 77_01753 |  |  |  |  | QC-TE Operation quality | To Be Reviewed |  | PL_77_1753 | 77_1753 |  | ISDP RolloutPlan | 38 | 2 | 0 | 0 | Site Cleanup QC plan | N |  |  | V2.6 |  | 2021-07-20 10:08:48 | 2021-07-20 10:18:50 | 2021-07-20 10:03:59 |  |  |  | N | [6 empty] | 2521642106 | Site Cleanup | MC |  | 2021-07-20 09:49:26 | 56A0A8L |  | Normal task
3002044831006 | 77_13976 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_13976 | 77_13976 |  | ISDP RolloutPlan | 7 | 7 | 6 | 0 | Site Cleanup QC plan | N |  |  | V1.100000 |  | 2021-05-29 09:44:04 | 2021-05-29 11:57:35 | 2021-05-29 11:34:34 | 2021-05-30 13:11:17 | 2021-05-30 13:13:25 |  | N | [6 empty] | 2514333106 | Site Cleanup | MO |  | 2021-03-26 13:10:18 | 56A0A8L |  | Owner changed | 2021-05-30 13:13:25 |  | 2021-05-30 13:11:17
3002046401006 | 77_12432 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_12432 | 77_12432 |  | ISDP RolloutPlan | 21 | 21 | 20 | 0 | Site Cleanup QC plan | N |  |  | V1.500000 |  | 2021-05-24 15:48:18 | 2021-05-24 19:02:58 | 2021-05-24 15:48:18 | 2021-05-24 19:34:03 | 2021-05-24 21:04:17 |  | N | [6 empty] | 2657448106 | Hardware installation | MC |  | 2021-04-18 13:07:57 | 56A0A8L |  | Normal task | 2021-05-24 21:04:17 |  | 2021-05-24 19:34:03
3002049654006 | 77_10324 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_10324 | 77_10324 |  | ISDP RolloutPlan | 11 | 11 | 7 | 4 | Lamp Pole Painting | N |  |  | V1.100000 |  | 2021-06-09 17:33:20 | 2021-07-05 19:33:28 | 2021-06-09 17:33:20 | 2021-06-09 19:42:52 | 2021-06-22 11:04:10 |  | N | [6 empty] | 11748830106 | Lamp Pole Painting | MC |  | 2021-05-20 16:16:31 | 56A0A8L |  | Normal task | 2021-06-22 11:04:09 |  | 2021-06-09 19:42:52
3002049982006 | 77_10012 |  |  |  |  | QC-TE Operation quality | Pass With Minor Issues |  | PL_77_10012 | 77_10012 |  | ISDP RolloutPlan | 9 | 9 | 8 | 1 | Site Cleanup QC plan | N |  |  | V1.900000 |  | 2021-06-21 09:39:08 | 2021-07-08 19:58:04 | 2021-06-21 09:39:08 | 2021-06-23 23:33:01 | 2021-07-08 19:58:04 |  | N | [6 empty] | 2234721106 | Site Cleanup | MC |  | 2021-05-22 19:45:31 | 56A0A8L |  | Normal task | 2021-06-23 23:35:39 |  | 2021-06-23 23:33:01
3002050594006 | 77_20132 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_20132 | 77_20132 |  | ISDP RolloutPlan | 10 | 10 | 9 | 0 | Site Cleanup QC plan | N |  |  | V1.900000 |  | 2021-05-27 15:38:29 | 2021-05-27 18:01:56 | 2021-05-27 15:38:29 | 2021-05-27 18:05:38 | 2021-05-27 18:06:54 |  | N | [6 empty] | 11843232106 | Site Cleanup | MC |  | 2021-05-27 13:54:36 | 56A0A8L |  | Normal task | 2021-05-27 18:06:54 |  | 2021-05-27 18:05:38
3002053497006 | 77_04770 |  |  |  |  | QC-TE Operation quality | Reviewing |  | PL_77_4770 | 77_4770 |  | ISDP RolloutPlan | 47 | 39 | 36 | 3 | Poles QC plan (ОДН) | N |  |  | V4.900000 |  | 2021-06-24 12:28:50 | 2021-06-28 22:28:51 | 2021-06-24 12:28:50 | 2021-06-24 13:25:22 | 2021-06-28 22:28:53 |  | N | [6 empty] | 2640462106 | Smart QC task(installation) | MO |  | 2021-06-23 21:30:00 | 56A0A8L |  | Normal task | 2021-06-28 22:28:53 |  | 2021-06-24 13:25:22
3002054057006 | 77_11425 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_11425 | 77_11425 |  | ISDP RolloutPlan | 47 | 41 | 28 | 13 | Poles QC plan (ОДН) | N |  |  | V5.000000 |  | 2021-06-29 21:27:18 | 2021-07-17 13:36:29 | 2021-06-29 21:27:18 | 2021-07-01 10:45:43 | 2021-07-17 14:42:16 |  | N | [6 empty] | 2336348106 | Smart QC task(installation) | MC |  | 2021-06-29 00:38:25 | 56A0A8L |  | Normal task | 2021-07-17 14:43:46 |  | 2021-07-01 10:45:43
3002054401006 | 77_20349 |  |  |  |  | QC-TE Operation quality | Rejected |  | PL_77_20349 | 77_20349 |  | ISDP RolloutPlan | 60 | 60 | 56 | 4 | Moscow SWAP QC Plan | Y | 2021-07-06 17:54:40 | 2021-07-06 17:54:59 | V3.600000 |  | 2021-07-06 17:54:39 | 2021-07-09 14:47:36 | 2021-07-06 17:54:39 | 2021-07-06 17:54:40 | 2021-07-09 15:58:43 |  | N | [6 empty] | 2580118106 | Smart QC task(installation) | MO |  | 2021-07-01 09:47:58 | 56A0A8L |  | Normal task | 2021-07-09 15:58:43 |  | 2021-07-06 20:02:54